## Sheet1
STA Action Items CR
Sl No | Screen | Requirements | Screen Changes New or Existing | Timeline | Relase Version
1 | Inward (Auto) | Document Subtype wants to create for Doc Type - Transmission,Loss of shares,IEPF Like Others Doc Type | Existing | 2 Hours | 1
2 | - | a) Automate Reverse feed from NSDL / CDSL for in-transit confirmation b) Share Capt = Benpos + In-transit confirmed + Physical (between Friday to Friday) |  |  | 3
3 | Inward (Auto) | TRANSMISTION ,ISR,OTHERS,CHANGE PAN rename as PAN UPDATE Except this(4) Doc type pan no validation No need If pan no is blank means it should allow inward otherwise we wants to check on debarrt master | Existing | Half Day/4 Hours | 1
|  | For inward Pan no is blank means Hard stop | Existing |  | 1
|  | Debarrt Pan Entry screen | New | 2 Days | 1
|  | Release Pan Entry Screen | New | 2 Days | 1
|  | Pan master wants to mainteane | New | Half Day/4 Hours | 1
4 | ISR Maker Entry | Debarrt Pan validation wants to implement | Existing | 1 Day | 1
| TRANSMISSION Maker Entry | Debarrt Pan validation wants to implement | Existing
| CHANGE PAN Maker Entry | Debarrt Pan validation wants to implement | Existing
5 | Debarrt Report | Before Voting Dedube Check(Report Wants to Take and give) | New |  | 2
6 | CDSL Rejection Upload | CDSL Rejection Upload |  |  | 3